## Bug List
Bug description | Version Found | Version Fixed
Cant add additional ingredients after the first. And the pjax reload not working correctly | 1.0.0
I am entering an order and wanted to put in a percentage which was not a round number and the system auto rounded up on me. This will need to be changed as a lot of additives are not whole numbers. Can we change this please | 1.0.0 | 1.0.1 | Modified View files accordingly
can't seem to get it to do the weighbridge ticket or print out or allow the despatching of the finished order. | 1.0.0 | 1.0.1
Set the delivery details page to read only when completed | 1.0.1 | 1.0.2
uncomplete a delivery needs to roll back to the last delivery details | 1.0.1 | 1.0.2
Add Anticpated Sales in Dashboard and menu item | 1.0.1 | 1.0.2
Add in the trailer name to the Paired with trailer screen not just the rego number | 1.0.5 | 1.0.6
Display the Trailer pair and tdefault truck in the index page for trailers | 1.0.5 | 1.0.6
Customer orer sheet displays XX in truck type | 1.0.5 | 1.0.6
Customer order sheet to be emailed on submit | 1.0.5 | 1.0.6
Customer Order sheet not displaying miling numbers or feed rte | 1.0.5 | 1.0.6

## Enhancements
Details | Requested | Added in Version
Add Daily Sales Figures (Client,Ordered,Dispatched,returned,difference) | 2016-05-01 | 1.0.3
Order State Widget | 2016-05-01 | 1.0.4
Add in the ability to change the delivery Qty as sepertate from the customer order | 2016-05-09 | 1.0.5
Change the default fill method to select bins first | 2016-05-09 | 1.0.5
Add in the label printing to the delivery sheet | 2016-05-09 | 1.0.5

## Versions
Version number | Git Hash
1.0.0 | c4e3fc7b76f83ffa51b64b4aa5fed0a05998c79d | Start of the user experience, bug tracking and versioning
1.0.1
1.0.2 | f36ffae9f7b9fe5ba2b4286e5bb90c03bd9fd721 | Finalised version before user testing
1.0.3 | 6410c4d660bd46c7dd1254e7d8204dd9235d92ef | Added Daily Sales figures screen
1.0.4 |  | Added the order status widget along the top
1.0.5 |  | Bug fixes (See Bug List) and adding the labels
1.0.6 |  | Added email Queues and minor bug fixes